## Introduction
Document Name | Communications Plan
Document Objectives | The objective of this document is to provide a communications plan for the first 90 days needed to support the OneMontclair Finance Program.
Document Description | This worksheet provides all the details for the communications that will need to take place over the course of the first 90 days of the OneMontclair program.
Communication Plan Elements
# | A unique numeric identifier for each communication
Message | A brief descriptive name for each communication message
Topics | A list of the content that will be addressed in the message
Media | Identification of the message delivery medium. Options include:
| Meeting In A Box | Presentations prepared for project representatives to deliver to their audience, including any supplemental handouts. Will be developed by the Communiations Team and provided to OneMontclair Liaisons approximately every 6 weeks to talk about project progress, key themes, and upcoming milestones. OM Liaisons will then deliver this prepared content to their audience via existing staff meetings.
| Email | Ad hoc email messages customizable by audience via distribution lists. These messages are typically milestone driven to alert audiences of completed or upcoming key events. All emails should be distributed via a dedicated OneMontclair email address (i.e., OneMontclair@montclair.edu) managed by the communications team.
| Poster | Large color posters designed for visual impact and communication of minimal, simple messages, and placed strategically across the MSU campus in locations designed for high traffic by affected business functions. These should be updated on a quarterly basis.
| Website | Updates of the OneMontclair website with the latest Pillar goals, progress, impacts, and frequently asked question content. This should be updated on a monthly basis.
Audience | A list of who will receive the message (by function, department, job, etc.)
Expected Publication | The target publication/distribution date for the communication.
Status | The status of the communication development/publication. Options include:
| Not Started | No work has been started on this communication
| In Development | Work has begun on this message (e.g., information gathering or initial writing), but a full initial draft of the message has not been completed
| In Review | An initial draft of the message has been completed, and the content is in the review/revision cycle with the content source or the Communications Lead
| Ready For Publication | The communication has been completed and approved by the Communication Lead, but has not yet been published/distributed
| Published | The communication has been published/distributed
| On Hold | Development/distribution of the communication has been put on hold
Content Source/ Reviewer | The name/role of the person who will provide the content for the message and review the draft for factual accuracy
Developer | The name of the person responsible for creating the communication
Publisher | The name/role of the person who will publish or deliver the message (e.g., OneMontclair Liaisons for Meeting In A Box; website developer for web updates)

## Communications Plan
Communications Plan: July 2014 - Sept 2014
# | Message | Topics | Media | Audience | Expected Publication | Status | Content Source/ Reviewer | Developer | Publisher
1 | OneMontclair Liaison Kickoff | ● OneMontclair Liaison selection and responsibilities/expectations ● How to successfully engage/communicate to stakeholders ● How to successfully solicit feedback from stakeholders ● How to communicate feedback to the OneMontclair Program/Pillars ● OneMontclair scope and expected benefits ● OneMontclair milestones and timeline | Meeting In A Box | OneMontclair Liaisons | 2014-07-28 | Not Started | Rob Luczak | TBD | Rob Luczak
2 | OneMontclair Announcement Email | ● OneMontclair milestones and timeline (update / inform on changes, if necessary) ● Update Pillar-specific milestones and timelines ● OneMontclair email address | Email | All Audiences | 2014-08-01 | Not Started | TBD | TBD | TBD
3 | OneMontclair Announcement Poster | ● OneMontclair scope and expected benefits ● OneMontclair milestones and timeline ● OneMontclair website address ● OneMontclair email address | Poster | All Audiences | 2014-08-01 | Not Started | Rob Luczak | TBD | OM Liaisons
4 | OneMontclair Website Refresh | ● OneMontclair scope and expected benefits ● OneMontclair milestones and timeline ● Pillar-specific scope, benefits, and expected audiences ● Pillar-specific milestones and timelines ● OneMontclair Frequently Asked Questions ● OneMontclair email address | Website | All Audiences | 2014-08-01 | Not Started | Pillar Leads | TBD | TBD
5 | OneMontclair Liaison Meeting | ● Stakeholder management Q&A - opportunity for OM Liaisons to receive feedback / guidance on how to engage stakeholders ● Inform Liaisons on any updates / changes to OneMontclair milestones and timeline ● Actions - key take aways for OM Liaisons (e.g., deliver face to face message to their audience) | Meeting In A Box | OneMontclair Liaisons | 2014-08-25 | Not Started | Rob Luczak | TBD | Rob Luczak
6 | OneMontclair Website Refresh | ● OneMontclair milestones and timeline (update / inform on changes, if necessary) ● Update Pillar-specific milestones and timelines ● Update OneMontclair Frequently Asked Questions, if needed | Website | All Audiences | 2014-09-01 | Not Started | Pillar Leads | TBD | TBD
7 | OneMontclair Email | ● OneMontclair milestones and timeline (update / inform on changes, if necessary) ● Update Pillar-specific milestones and timelines ● OneMontclair email address | Email | All Audiences | 2014-09-08 | Not Started | TBD | TBD | TBD
8 | OneMontclair Liaison Meeting | ● Stakeholder management Q&A - opportunity for OM Liaisons to receive feedback / guidance on how to engage stakeholders ● Inform Liaisons on any updates / changes to OneMontclair milestones and timeline ● Actions - key take aways for OM Liaisons (e.g., deliver face to face message to their audience) | Meeting In A Box | OneMontclair Liaisons | 2014-09-29 | Not Started | Rob Luczak | TBD | Rob Luczak
9 | OneMontclair Website Refresh | ● OneMontclair milestones and timeline (update / inform on changes, if necessary) ● Update Pillar-specific milestones and timelines ● Update OneMontclair Frequently Asked Questions, if needed | Website | All Audiences | 2014-10-06 | Not Started | Pillar Leads | TBD | TBD

## Data (hidden)
Media | Status
Meeting In A Box | Not Started
Email | In Development
Poster | In Review
Website | Ready For Publication
Published
On Hold