Sales Synergy Data Warehouse

Project Description

# The existing Sales & Marketing Data Mart (2000) is technologically obsolete and exceeding capacity. Rather than replace it with a similarly isolated new Sales & Marketing Data Mart, Synergy will implement a Sales & Marketing Data Mart using a framework that will support an Enterprise Data Warehouse. This framework uses Oracle Warehouse Builder, Kalido Dynamic Information Warehouse and Kalido Master Data Management which can be used to integrate information across all functional areas of the company.

# The existing Sales & Marketing Business Intelligence Reporting (2000) is also technologically obsolete and unsupported. New Business Intelligence Reporting for Sales & Marketing will provide the ability to distribute standard operation reports, to analyze pre-built cubes (the intersection of characteristics and measurements), to drill-down to the transactional detail, and to delivery personalized information on request through reports, dashboards and scorecards. This functionality is provided by MicroStrategy Business Intelligence. MicroStrategy Business Intelligence will be available to all functional areas of the company that are integrated into the Enterprise Data Warehouse as well as to individual applications.

Scope

ESI Sales and Marketing Data User Groups

ESI Sales Planning and Analysis (6 Users)

ESI Market Research and Business Analytics (8 Users)

ESI Brand Analysts (21 Users)

ESI Sales and Brand Management (24 Users)

ESI District Managers and Regional Sales Directors (85 Users)

Business Benefits

- Value Proposition

  - Eliminate repetitive sales data loads, data validation, reduce man hours

  - Enhanced reporting and improved analytics that will facilitate more timely and appropriate decision making

  - Consistent information used across functional areas

- Business Drivers

- Reliability – Less down time

- Accurate/Consistent - No re-validation of data across systems

- Supportable/Upgradeable – Standard IT support

- Critical Outputs

- Less load time, more time on analytics – Focus on business issues not system issues

- Faster data and report delivery – Quicker turnaround

- Data available to other systems – Cross functional utilization of information

Position in Strategy

Incremental Revenue/Cost Savings (Business Process Enhancement, Integration)

Continued Operations (Capacity/Infrastructure Expansion, Patches, Upgrades)

Safety or Regulatory Compliance (Part 11, JSOX, OFCCP, etc.)

New Products (New Systems, Pioneering Business Process)

| ESI Data Warehouse CORFITA07002 | Completion Date: 10/25/2008 Total Percent Complete: 98.9% (Financial Expenditure Basis) | Project Phase (Underline) and condition: Plan>>Specify>>Design>>Develop>>Test >>Release>>Retire | Project Status 4 October 2008 |  |
| --- | --- | --- | --- | --- |

| Project Resources |
| --- |
| Project Manager (ECA-US): | Expenditures to Date (Forecast)/Actual |
| xxx xxx Kwan zzzz Consultant | Training ($102,454): Travel (): Maintenance ($398,345): Other(): | $66,482 $0 $ |
| Project Timeline | Capital Investments to Date (Forecast)/Actual |
| Original Start Date: 06/19/2007 Original End Date: 05/02/2008 Actual Start Date: 06/19/2007 Current End Date: 10/25/2008 | HW ($698,800): SW ($756,500): Contractor:($2,679,297): Services (): Other(): | $535,300 $901,538 $2,631,076 $0 $0 |

| Project Description |
| --- |
| This project includes implementation of a Data Warehouse and Business Intelligence reporting environment to replace the existing Sales and Marketing Data Mart (SMART) which is obsolete (1999) using a framework that will support an Enterprise Data Warehouse which can be configured to integrate information across all functional areas of the company. |
| Key Milestones / Deliverables | Planned Completion Date MM/DD/YY | Actual or Estimated Completion Date |
| Project Start: |  |  |
| Project Plan | 7/13/07 | 7/13/07 |
| BI Software Selection | 10/18/07 | 11/12/08 |
| DW Business Requirements | 10/29/07 | 10/29/07 |
| Architecture Design Specification | 11/13/07 | 11/13/07 |
| DW Development Specifications | 12/19/07 | 12/19/07 |
| BI Business Requirements | 1/2/087 | 1/4/08 |
| UAT Plan | 1/18/08 | 4/24/08 |
| BI Development Specifications | 2/11/08 | 2/11/08 |
| DW HW SW Implementation | 2/13/08 | 5/15//08 |
| BI HW SW Implementation | 3/13/08 | 6/3/08 |
| DW Development | 3/31/08 | 4/29/08 |
| BI Development | 4/21/08 | 5/14/08 |
| System Integration Testing | 4/23/08 | 7/8/08 |
| UAT | 4/23/08 | 7/25/08 |
| Production Migration | 4/24/08 | 8/13/08 |
| Parallel Testing - Month 1 | 5/1/08 | 8/29/08 |
| Parallel Testing - Month 2 | 5/7/08 | 9/26/08 |
| Parallel Testing - Month 3 |  | 10/25/08 |
| Status Summary for Monthly Report |
| ZS Associates Compensation Files delivered. Completed Parallel Testing of Month 2. |

| Status Highlights |
| --- |
| Budget |  | Resources |  | Technology/Architecture |  |
| Scope |  | Schedule |  | Vendor |  |

Key Issues (Explanation required for each At-Risk/Yellow or Critical/Red Status above)

Issues Resources – Turnover in consulting firm’s and XXX’s staff. Schedule – Dependent on IMS delivery of correct data. Vendor – IMS delivery of DDD Hospital and Xponent PlanTrak data. Each delivery of incorrect data delays the project by 1 month. Items Needing Management Attention (Red Items) None

Major Accomplishments/Decisions (Since last scorecard update)

Deliverable Owner Date Complete Parallel Testing - Month 2 Alliance 9/26/08

Planned Activities/Decisions

Deliverable Owner Date Complete Parallel Testing - Month 3 Alliance 10/25/08 Planned Project Cash Flow: Total Capital = $ 4,194,142 Total Expense = $ 0 Actual Project Cash Flow to date: Total Capital = $ 4,067,914 Total Expense = $ 66,482 Estimate to Complete: Capital = $ 59,746 Expense = $ 0

# Text boxes

Y

G

G

Y

G

Y

Y