## Instructions
OneMontclair Requirements Traceability Matrix Instructions | Revision Status
| Firm | New or Existing Requirement - Stable
| Firm but Changed | Stable Requirement Changed this Month
| Need info | Requirement not stable - need more info.
Template - v0.3 | CR Submitted | Stable Requirement needs to change
| Req is TBD | Placeholder - Requirement not defined
| Req. Complete | No further work required to implement
| Req Deleted | Requirement deleted this month
Requirement Types: BRnnn - Business Requirement FRnnn - Functional Requirement BZnnn - Business Rule DRnnn - Data Requirement NFnnn - Non-Functional Requirement UCnnn - Use Case
Field Descriptions
Field - Area / Group - Defined by the project - used to group or sort requirements by function or any other grouping.
Field - Requirements Source Document - The document file name where the requirement was defined.
Field - Req. ID - The unique identiffying number for the requirement - use the two letter codes defined above [Ref. OM-Template - Business Requirements Document (BRD)].
Field - Trace From Higher Level Requirement - For every derived requirement that is traceable to a higher level requirement, enter the Requirement ID for the higher level requirement. You can enter multiple Requirement IDs here to trace the current requirement to several higher level requirements.
Field - Requireent Description - This is the requirement itself - use the SMART criteria to define testable requirements [Ref. OM-TRN-004 - Requirements Training].
Field - Requirement Risk Rating - This sets the risk to the project if this requirement is not met - listed as "H", "M", or "L" for High, Medium, and Low.
Field - Original Requirement Date - This is the date the Requirement was originally agreed to. Usually the publish date of the source document.
Field - Revision Status - This is a drop-down pick list with the values and descriptions listed at the top of this worksheet.
Field - Status Date - If the status of a requirement changes, enter the date it was changed.
Field - CSCI, Module, or Sub-System - Identify the module or sub-system in which this requirement is implemented - use the application name if the requirement is addressed at the application level. A requirement may be duplicated to map it to multiple modules or sub-systems.
Field - Design Document(s) / Process Descriptions - List the file name(s) containing the design that relates to this requirement.
Field - Trace to Project Test Case ID - Enter the Test Case ID or file name that will test this requirement [Ref. OM-GUID-004].
Field - Trace to Test Summary Report (file name) - Enter the file name of the Test Summary Report that is the record of the test being completed.
Field - Test Summary Report Date - Enter the date for the Test Summary Report that first confirms this requirement is successfully implemented.
Field - Planned Release ID - Enter the release version or identification in which this requirement is planned to be implemented.
Field - Actual Release ID - Enter the release identification (product plus version) in which this requirement was successfully implemented and accepted via a Validation Summary Report.
Instructions:
1 - First go to the Approved Requirements worksheet - go to [PAGE LAYOUT] - [PRINT TITLES] - [HEADER / FOOTER] and replace "<< Project Name >>" with your project's name. Also replace "<< Project Name >>" with your project's name at the top of the worksheet (Cell D2).
2 - Copy in the requirements from the Project's Business Requirements Document. Read the Field Descriptions on the left of this page to guide your entries
3 - If the source document for a requirement has been baselined and approved, then set the Revision Status field to "Firm". Otherwise, set the field to Req. is TBD or Need Info as appropriate until the requirement is firm and approved.
4 - Enter appropriate Trace From ... values to indicate how derived requirements are traced to higher level requirements.
5 - Identify the Computer Software Configuration Item (CSCI) or Module or Sub-System in which the requirement will be implemented. If a requirement is mapped to multiple modules, then duplicate the requirement on a line for each module it is linked to. Also enter the Planned Release ID in which this requirement is expected to be met.
6 - As designs are completed, enter the Design Document / Process Description names.
7 - As Test Cases are developed and traced to these requirements, enter the Project Test Case ID in that field for each requirement.
8 - If a requirement changes or needs to be changed - update the Revision Status field and Status Date field - this will help determine requirement volatility for your project. When a changed requirement is approved, set its status to Firm but Changed and enter the date in the Status Date field.
9 - As Test Cases are completed and approved, enter the name of the Test Report and date of the Test and the Requirements First Implemented in Release ID field.
TRACK SIGNIFICANT UPDATES TO THIS DOCUMENT IN THE RTM CHANGE HISTORY WORKSHEET

## Approved Rqmnts
v0.3 |  | Project: | << Project name >> |  |  | See descriptions of these fields in the Instructions worksheet
Rec. # | Area / Group | Req Source Document | Req ID BRnnn FRnnn BZnnn DRnnn NFnnn Ucnnn | Trace From Higher Level Requirement | Requirement Description | Requirement Risk Rating | Original Req Date | Revision Status | Status Date | CSCI, Module, or sub-system | Design Document(s) / Process Descriptions | Trace to Project Test Case ID | Trace to Test Summary Report (filename) | Test Summary Report Date | Planned Release ID | Actual Release ID
1 |  | OM-FIN_BRD_v2.0 | BR001 |  | Business Requirement One | H | 2014-04-05 | Firm | 2014-03-14 | bugzilla |  |  |  | 2014-03-17 |  | bugzilla v3.9.5
|  | OM-FIN_BRD_v2.0 | FR001 | BR001 | Functional Requirement One | M | 2014-04-05 | Firm but Changed | 2014-03-14 | bugzilla | [5 empty] | bugzilla v3.9.5
|  | OM-FIN_BRD_v2.0 | DR001 | FR001 | Data Requirement One | L | 2014-04-05 | CR Submitted | 2014-03-14 | bugzilla | [5 empty] | bugzilla v3.9.5
Req is TBD
Req. Complete
Req Deleted
<< Add Requirements Above This Line >>

## RTM Change History
RTM Version Number | RTM Date | RTM Description | Updated by:
v 1.0 | 2014-05-05 | Initial Document | << Project Manager Name >>